## Assignments
Project Task TRACKER
Services | Task | docs required | task type | Faculty Assigned | Status | Start date | Due on | Finished date | Days Taken | remarks
admission | Admission flow creation management |  | developing | Aleena Varghese | Done
admission | Admission flow creation merit |  | developing | Aleena Varghese | Done
course | course creation |  | developing | George Sebastian | Done
timetable | timetable creation |  | developing | Ashwin | Done
timetable | timetable faculty view |  | developing | Ashwin | Done
timetable | timetable student view |  | developing | Ashwin | Done
admission | Admission flow creation management |  | testing | Nicy Johnson | Done
admission | Admission flow creation merit |  | testing | Joshua Sony | Done
timetable | timetable history |  | developing | Ashwin | Done
course plan | first version of courseplan |  | developing | George Sebastian | Done
timetable | testing timetable |  | testing | Nicy Johnson | In progress | 2026-07-21 | 2026-07-24
timetable | timetable fix - special timetable |  | developing | Ashwin | In progress | 2026-07-21 | 2026-07-24
calendar | calendar creation with events |  | developing | Aleena Varghese | In progress | 2026-07-21 | 2026-07-24
course plan | correcting the course plan as per new curriculum |  | developing | George Sebastian | In progress | 2026-07-21 | 2026-07-24
admission | supporting merit admission |  | debugging | Livya George | Done | 2026-07-20 | 2026-07-22
course | courses creation - header, syllabus, module contents, approval |  | testing | Anugraha K R | In progress | 2026-07-21
curriculum | curriculum creation and approval |  | testing | Anugraha K R | In progress
course plan | course plan creation, approval and versioning |  | testing | Livya George | Not started | 2026-07-22 | 2026-07-24
leave | leave types creation | Leave Procedure Sahrdaya casual leave.pdf (casual leave ISO format) TR 04(02) Staff Training External Programs Request Form.pdf 2024-25 Leave.xlsx | developing | Aleena Varghese
leave | leave flow creation |  | developing | Aleena Varghese
course-offerings | course registration- student side |  | developing | select | Not started
course-offerings | course registration admin side (allocation) for program electives,global electives, honours and minors. |  | developing | select | Not started
exam | End sem exam registration with payment |  | developing | select | Not started
exam | End sem exam creation |  | developing | select | Not started
payments | payment management (office) |  | developing | select | Not started
user-management | fix errors |  | debugging | select | Not started
assessment | creation, entry of rubrics or marks |  | developing | select | Not started
OBE | obe calculation from course | EST102_2021-22AY_CO Attainment.xlsx CSA2019_CSL332 NPLAB Attainment Lab.xlsx | developing | select | Not started
OBE | obe calculation overall batchwise, Academic yearwise - weightage to be given | CO-PO Attainments 2021-22.xlsx | developing | select | Not started
OBE | indirect attainment calculation courses |  | developing | select | Not started
OBE | indirect attainment calculation overall ( alumni, employer,etc) with weightage | Copy of FEEDBACK FROM PARENTS conducted during 2020-21 (Responses).xlsx | developing | select | Not started
OBE | reports - batchwise and academic yearwise |  | developing | select | Not started
course File | creation, approval, print - theory course | COURSE FILE INDEX-THEORY.docx COURSE FILE INDEX.pdf | developing | select | Not started
course File | creation, approval, print - Lab course | COURSE FILE INDEX lab .docx | developing
course File | creation, approval, print - seminar course | COURSE FILE INDEX-Seminar.docx | developing
course File | creation, approval, print - project course | COURSE FILE INDEX-Project.docx | developing
course File | creation, approval, print - theory+lab course | theory and lab details in one file | developing
| creation, approval, print - theory+project course | theory and project details in one file | developing
Feedback Management | Teacher Evaluation Feedback | student feedback1 (1).doc student feedback report_consolidation_faculty_print.pdf | developing | select | Not started
Feedback Management | Infrastructure Feedback |  | developing | select | Not started
Feedback Management | Course Exit Surveys (centralised coursewise) | Course End Evaluation_Format.doc | developing | select | Not started
Feedback Management | Interim CAT Feedbacks(centralised coursewise) | Interim Course Evaluation_Format.doc | developing |  | Not started
Feedback Management | graduate exit survey | Graduate Exit Survey.doc | developing |  | Not started
Feedback Management | Parent Survey | Feedback from Parents.docx | developing
Feedback Management | Alumni Survey | Alumni Sahrdaya Feedback.doc | developing
Feedback Management | resource persons feedback | Resource persons feedback - Department.doc | developing
Feedback Management | employer feedback | PL 05A(00) Employer feedback.docx | developing
Feedback Management | student satisfaction survey | SSS-Questinnaire_Students (1).pdf | developing
exam | External Lab exam creation, timetable , mark entry |  | developing | select | Not started
exam | Internal Lab exam creation, timetable , mark entry |  | developing | select | Not started
Reports | advisors record | AC 17 (02) Advisors Record on students performance.xlsx | developing | select | Not started
Reports | Internal Exam Result Analysis | AC 36A (02)CAT Result Analysis.pdf | developing | select | Not started
Reports | End semester Exam Result Analysis | AC 36E(00) UNIVERSITY RESULT ANALYSIS(2019 Scheme).xlsx | developing | select | Not started
Reports | subject allocation | AC 01A(02) Subject Allocation.xlsx | developing | select | Not started
Reports | faculty workload | AC 01C(01) Faculty Workload.xlsx | developing
Reports | tutorial log book | AC 49(00) Tutorial Logbook.doc | developing | select | Not started
Reports | monthly report | AC 13 (04) Monthly Report of HoDs.doc | developing | select | Not started
Reports |  |  | developing | select | Not started
Reports | slow learners coaching schedule | AC 33(04) Slow Learners Coaching Schedule.xlsx | developing | select | Not started
Reports | API | HR 17(00) Annual Performance Index (20-21).xlsx | developing | select | Not started
Reports | faculty feedback department consolidation | BT 2019-20 EVEN consolidated_evaluation_report.xlsx - Google Sheets.pdf | developing | select | Not started
Reports | feedback survey reports | PollsAndSurveyReport.xls Polls and survey.pdf Polls and survey (2).pdf | developing | select | Not started
library | library books creation |  | developing | select | Not started
library | library books issue |  | developing | select | Not started
library | library books fine |  | developing | select | Not started
library | library books user side view |  | developing | select | Not started
library | library books admin side view |  | developing | select | Not started
placement |  |  | developing | select | Not started
service-registry | RBAC authorization middleware + service management UI |  | developing | George Sebastian | Done | 2026-05-23 |  | 2026-05-25 | 3 | original scope
class-management | class management module: backend, student view, assign faculty/students |  | developing | George Sebastian | Done | 2026-05-29 |  | 2026-06-18 | 21 | original scope; academic year + live student data
syllabus-parser | syllabus parser for course import (.tex/.docx) |  | developing | George Sebastian | Done | 2026-06-01 |  | 2026-06-01 | 1 | original scope
course | course creation: create / import / edit — frontend + backend |  | developing | George Sebastian | Done | 2026-06-02 |  | 2026-06-12 | 11 | original scope; course master + SLO fix
academic-management | academic management backend + academic years |  | developing | George Sebastian | Done | 2026-06-10 |  | 2026-06-18 | 9 | original scope; all data access via backend
user-management | bulk employee importer + user directory fixes |  | debugging | George Sebastian | Done | 2026-06-10 |  | 2026-06-12 | 3 | fixes to deployed module
responsibility-groups | responsibility groups: creation + RBAC frontend enforcement |  | developing | George Sebastian | Done | 2026-06-15 |  | 2026-06-25 | 11 | original scope
course | course approval flow rework + coordinator decoupled from syllabus in-charge |  | developing | George Sebastian | Done | 2026-06-23 |  | 2026-06-29 | 7 | REQ CHANGE after deploy: flow restructure + DQSC step + decoupling requested after initial flow was approved
course plan | first version of course plan (Part 4: hour-by-hour, model ESE paper) |  | developing | George Sebastian | Done | 2026-06-17 |  | 2026-07-08 | 22 | original scope; incl. moving hour-by-hour from Part 3 to Part 4 (structure change requested mid-build)
| GCP build pipeline fix + stale website cache fix |  | debugging | George Sebastian | Done | 2026-06-18 |  | 2026-06-19 | 2 | infra fixes on deployed app
curriculum | curriculum credit matrix + permission/edit fixes |  | developing | George Sebastian | Done | 2026-07-01 |  | 2026-07-02 | 2 | REQ CHANGE after deploy: credit matrix requirement added after curriculum module was live
curriculum | curriculum approval workflow creation (HoD → IQAC chain) |  | developing | George Sebastian | Done | 2026-07-02 |  | 2026-07-13 | 12 | REQ CHANGE after deploy: approval chain requirement added after curriculum module was deployed
course | course PDF exporter |  | developing | George Sebastian | Done | 2026-07-03 |  | 2026-07-10 | 8 | REQ CHANGE after deploy: export requirement raised after course module was approved
course | course archive/unarchive + faculty dropdown + title-case rules |  | developing | George Sebastian | Done | 2026-07-04 |  | 2026-07-04 | 1 | REQ CHANGE after deploy: naming rule reversed same week (camelCase then Title Case)
curriculum | curriculum PDF export + preface step |  | developing | George Sebastian | Done | 2026-07-08 |  | 2026-07-10 | 3 | REQ CHANGE after deploy: export + preface requirements raised after module was live
curriculum | elective tracks (Step 7) + slot-grouped elective credits |  | developing | George Sebastian | Done | 2026-07-13 |  | 2026-07-17 | 5 | REQ CHANGE after deploy: track model + same-slot credit rule defined after curriculum was approved
course | assessment pattern rework (ESE from header, totals, validation) |  | developing | George Sebastian | Done | 2026-07-13 |  | 2026-07-21 | 9 | REQ CHANGE after deploy: ESE handling respecified after course creation was deployed and approved
course plan | embed Course Builder as §4.2–4.3, single SLO store |  | developing | George Sebastian | Done | 2026-07-17 |  | 2026-07-17 | 1 | REQ CHANGE after deploy: CO/SLO restructure decided after course plan v1 was approved
curriculum | curriculum approval fixes: HoD→IQAC routing, edit lock, approver access |  | developing | George Sebastian | Done | 2026-07-21 |  | 2026-07-23 | 3 | part fix, part REQ CHANGE: edit-lock and approver-access rules decided after workflow was live
course plan | per-batch course plan variants (one plan per course+batch, versioned) |  | developing | George Sebastian | Done | 2026-07-22 |  | 2026-07-22 | 1 | REQ CHANGE after deploy: one-plan-per-course changed to per-batch after course plan was deployed and approved
course plan | per-batch authoring surface: author in Classes, approve in Class Management |  | developing | George Sebastian | Done | 2026-07-24 |  | 2026-07-25 | 2 | REQ CHANGE after deploy: authoring moved out of the course wizard; per-batch coordinator ownership
course | non-taught course types: syllabus mandatories made optional (Thesis, MOOC, Project…) |  | developing | George Sebastian | Done | 2026-07-24 |  | 2026-07-24 | 1 | REQ CHANGE after deploy: relaxation requested after wizard was approved
course plan | editor fixes: Save Draft freeze, CO/SLO/micro-SLO editing, blank-content rules dropped |  | debugging | George Sebastian | Done | 2026-07-27 |  | 2026-07-27 | 1 | part fix, part REQ CHANGE: owner rule that nothing typed is mandatory
course | wizard fixes: ESE row in submit gate + exported PDF, status display, edit lock, stale UI |  | debugging | George Sebastian | Done | 2026-07-27 |  | 2026-07-28 | 2 | fixes on deployed module
| app reload diagnostics: record why the app reloads itself instead of reloading silently |  | debugging | George Sebastian | Done | 2026-07-27 |  | 2026-07-27 | 1 | silent random reloads were unreportable before
classes | class header shows L-T-P-C + card fixes (coordinator tag, full course title) |  | debugging | George Sebastian | Done | 2026-07-28 |  | 2026-07-30 | 3 | coordinator tag never appeared — query filtered on a column it never selected
course plan | CO Mappings (§4.5) split into its own HoD-approved document + section renumbering |  | developing | George Sebastian | Done | 2026-07-29 |  | 2026-07-29 | 1 | REQ CHANGE after deploy: matrices left the plan for their own approval chain
course plan | coordinator-only authoring + Lab Experiments §4.8 restored |  | developing | George Sebastian | Done | 2026-07-29 |  | 2026-07-29 | 1 | REQ CHANGE + fix: every step-3 save was silently deleting the experiment list
assessment | Assessment Studio imports Course Plan assessments once their SLO is covered |  | developing | George Sebastian | Done | 2026-07-29 |  | 2026-07-29 | 1 | new requirement post-deploy: teach first, assess second — enforced at the picker
course-companion | Companion + P-E-L-C board run the HoD-approved per-batch plan |  | developing | George Sebastian | Done | 2026-07-29 |  | 2026-07-30 | 2 | REQ CHANGE after deploy: student runtime rebased from legacy plan onto per-batch plan
curriculum | export changes: handbook stops at Part 2, progress modal, revision-request checklist |  | developing | George Sebastian | Done | 2026-07-29 |  | 2026-07-30 | 2 | REQ CHANGE after deploy: owner cut Module Contents from the handbook export
course plan | export/import a version's chain as a portable JSON file |  | developing | George Sebastian | Done | 2026-07-30 |  | 2026-07-30 | 1 | new requirement post-deploy: author in a dummy class, import into the real one
class-management | Assign Faculty: Course Coordinator pool widened to the same course in other batches |  | developing | George Sebastian | Done | 2026-07-30 |  | 2026-08-01 | 3 | new requirement post-deploy: common first-sem courses share one coordinator
course plan | HoD can unlock an approved plan — content in use stays frozen |  | developing | George Sebastian | Done | 2026-07-31 |  | 2026-07-31 | 1 | REQ CHANGE after deploy: post-approval editing added, with freeze rules for taught/assessed content
| nightly database backups: run, review, reschedule + streamed downloads from System Management |  | developing | George Sebastian | Done | 2026-08-01 |  | 2026-08-01 | 1 | new infra requirement; signed URLs impossible on Cloud Run so downloads stream through the server
staff-attendance | COSEC biometric push + collect-everything-publish-nothing-until-reviewed switch |  | developing | George Sebastian | Done | 2026-08-01 |  | 2026-08-01 | 1 | new requirement: punches collected from day one, hidden from staff until reviewed
curriculum | detail view: on-screen blueprint tables, per-course IQAC review, read-only wizard popup |  | developing | George Sebastian | Done | 2026-08-01 |  | 2026-08-01 | 1 | REQ CHANGE after deploy: detail view redesigned twice on owner request — PDF embed added then dropped same day
curriculum | Mandatory Courses step: a course taken once in any allowed semester, with exam slot |  | developing | George Sebastian | Done | 2026-08-03 |  | 2026-08-03 | 1 | REQ CHANGE after deploy: new wizard step added after curriculum was approved
curriculum | Course Requisites step: soft/hard/co-requisites per curriculum, locked into course wizard |  | developing | George Sebastian | Done | 2026-08-04 |  | 2026-08-04 | 1 | REQ CHANGE after deploy: new wizard step; curriculum now owns the course prerequisite field
class-management | class management frontend: classes list UI, batch and class-section creation |  | developing | Ashwin | Done | 2026-05-29 |  | 2026-06-01 | 4 | original scope
dashboard-feed | dashboard shell: sidebar icons, layout and navigation bug fixes |  | debugging | Ashwin | Done | 2026-06-02 |  | 2026-06-02 | 1 | fixes on deployed shell
mission-vision | PEO / WK / PSO manager screens |  | developing | Ashwin | Done | 2026-06-02 |  | 2026-06-04 | 3 | original scope
course | course creation UI: create and edit screens, plus fixes |  | developing | Ashwin | Done | 2026-06-05 |  | 2026-06-10 | 6 | original scope
dashboard-feed | faculty dashboard: initial cards and layout |  | developing | Ashwin | Done | 2026-06-10 |  | 2026-06-10 | 1 | original scope
class-management | Assign Faculty UI and faculty-course mapping screens |  | developing | Ashwin | Done | 2026-06-11 |  | 2026-06-17 | 7 | original scope
curriculum | curriculum edit feature (frontend) |  | developing | Ashwin | Done | 2026-06-12 |  | 2026-06-12 | 1 | original scope
attendance | attendance marking UI - first version |  | developing | Ashwin | Done | 2026-06-15 |  | 2026-06-15 | 1 | original scope
user-management | user directory and user-edit UI fixes |  | debugging | Ashwin | Done | 2026-06-16 |  | 2026-06-16 | 1 | fixes on deployed module
classes | classes module UI: class and course views, live student list fetch |  | developing | Ashwin | Done | 2026-06-17 |  | 2026-06-22 | 6 | original scope
course plan | wire the Course Plan view into Classes and fix plan fetching |  | developing | Ashwin | Done | 2026-06-18 |  | 2026-06-19 | 2 | original scope
assessment | assessment UI fixes |  | debugging | Ashwin | Done | 2026-06-19 |  | 2026-06-23 | 5 | fixes on deployed module
timetable | manual timetable builder - first version: weekly grid, period assignment |  | developing | Ashwin | Done | 2026-06-24 |  | 2026-06-29 | 6 | original scope
elective-timetable | elective periods in the timetable grid |  | developing | Ashwin | Done | 2026-06-25 |  | 2026-06-25 | 1 | original scope
timetable | timetable builder updates and UI fixes |  | developing | Ashwin | Done | 2026-07-01 |  | 2026-07-04 | 4 | original scope
rooms | Rooms service: room master creation |  | developing | Ashwin | Done | 2026-07-02 |  | 2026-07-02 | 1 | new requirement: timetable needs a room register
timetable | student timetable view |  | developing | Ashwin | Done | 2026-07-06 |  | 2026-07-06 | 1 | original scope
assessment | assessment UI update and student assessment flow |  | developing | Ashwin | Done | 2026-07-07 |  | 2026-07-10 | 4 | original scope
attendance | attendance UI fixes and lab-batch UI |  | debugging | Ashwin | Done | 2026-07-09 |  | 2026-07-10 | 2 | fixes on deployed module
timetable | special timetable fix, period management, faculty workspace grid |  | developing | Ashwin | Done | 2026-07-13 |  | 2026-07-16 | 4 | part fix, part REQ CHANGE: special-day timetables
timetable-coordinators | timetable coordinator role: department-scoped assignment |  | developing | Ashwin | Done | 2026-07-17 |  | 2026-07-17 | 1 | new requirement post-deploy: scoped coordinator instead of a designation
attendance | attendance flow rework and updates |  | developing | Ashwin | Done | 2026-07-19 |  | 2026-07-20 | 2 | original scope
timetable | timetable fixes |  | debugging | Ashwin | Done | 2026-07-20 |  | 2026-07-20 | 1 | fixes on deployed module
classes | class advisors system with auto-split and attendance UI |  | developing | Ashwin | Done | 2026-07-22 |  | 2026-07-22 | 1 | new requirement post-deploy
timetable | effective-window publishing and Special Days Log module |  | developing | Ashwin | Done | 2026-07-22 |  | 2026-07-22 | 1 | REQ CHANGE after deploy: a version must apply only inside its window
attendance | SLO-based coverage on the marking screen, live-period-only marking |  | developing | Ashwin | Done | 2026-07-22 |  | 2026-07-22 | 1 | REQ CHANGE after deploy: mark what was taught, not just who attended
attendance | per-course attendance threshold policies and eligibility |  | developing | Ashwin | Done | 2026-07-23 |  | 2026-07-23 | 1 | new requirement post-deploy
attendance | attendance feature suite: thresholds, disputes and mobile marking |  | developing | Ashwin | Done | 2026-07-23 |  | 2026-07-23 | 1 | original scope
attendance | attendance corrections workflow (faculty requests, class teacher decides) |  | developing | Ashwin | Done | 2026-07-23 |  | 2026-07-23 | 1 | new requirement post-deploy
rooms | per-room timetable - what each room is actually assigned |  | developing | Ashwin | Done | 2026-07-23 |  | 2026-07-23 | 1 | new requirement post-deploy
attendance | student attendance week and history views, incl. split labs and tutorials |  | developing | Ashwin | Done | 2026-07-24 |  | 2026-07-30 | 7 | original scope
attendance | session-type read-only, attendance PDF export and UX fixes |  | debugging | Ashwin | Done | 2026-07-24 |  | 2026-07-24 | 1 | fixes on deployed module
timetable | clash detection by wall-clock time, across timetable and attendance |  | debugging | Ashwin | Done | 2026-07-24 |  | 2026-07-24 | 1 | fix on deployed module: clashes were compared by period number
timetable | timetable readiness check, publish guard and holiday attendance |  | developing | Ashwin | Done | 2026-07-25 |  | 2026-07-25 | 1 | original scope
timetable | split-session fixes end to end - student view, labels, room gate |  | debugging | Ashwin | Done | 2026-07-26 |  | 2026-07-26 | 1 | fixes on deployed module
classes | Academic Responsibilities section: naming, faculty match, search |  | debugging | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | fixes on deployed module
attendance | mark only your own batch; read the approved per-batch course plan |  | developing | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | REQ CHANGE after deploy: coverage rebased on the approved plan
attendance | per-micro-SLO progress and one rule for what coverage is still owed |  | developing | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | REQ CHANGE after deploy: progress asked for at micro-SLO level
system-config | 12-hour time display everywhere - one renderer, client and server |  | developing | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | new requirement post-deploy
timetable | builder: an empty catalog is not a departed teacher; manual faculty test switch retired |  | debugging | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | fixes on deployed module
timetable | a version is served only for the semester it was built for |  | debugging | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | fix on deployed module
timetable-coordinators | coordinators reach Class Management, scoped to their own departments |  | developing | Ashwin | Done | 2026-07-27 |  | 2026-07-27 | 1 | new requirement post-deploy
classes | class cards: course header facts, scrutiny exclusion, attendance grid tone/z-index |  | debugging | Ashwin | Done | 2026-07-28 |  | 2026-07-29 | 2 | fixes on deployed module
dashboard-feed | faculty dashboard/attendance refresh; split-batch Faculty picker clearing on click |  | debugging | Ashwin | Done | 2026-07-28 |  | 2026-07-28 | 1 | fixes on deployed module
timetable | Drafts: no "no drafts yet" flash, institute-wide data cached, room warning deferred |  | debugging | Ashwin | Done | 2026-07-28 |  | 2026-07-28 | 1 | fixes on deployed module
class-management | Assign Faculty: stamp each course with its OWN semester, not the open one |  | debugging | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | fix on deployed module
attendance | marking bar stops inventing a register that does not exist |  | debugging | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | fix on deployed module
attendance | SLO coverage made mandatory, multi-select and fixable after the fact |  | developing | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | REQ CHANGE after deploy
attendance | only course faculty may mark a register |  | developing | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | fix on deployed module: marking was open too widely
classes | class roster shows three student identifiers, not one fallback chain |  | debugging | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | fix on deployed module
classes | course coverage: show the SLO tree, not a flat table |  | developing | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | REQ CHANGE after deploy
timetable | faculty hour swaps: mutual-consent period cover, one date at a time |  | developing | Ashwin | Done | 2026-07-29 |  | 2026-07-29 | 1 | new requirement post-deploy
timetable | offer New timetable in Class Management; weekly grid scrolls instead of crushing |  | developing | Ashwin | Done | 2026-07-30 |  | 2026-07-30 | 1 | new requirement post-deploy
timetable | tutorial faculty split: ask, deduce, and let the pair be swapped |  | developing | Ashwin | Done | 2026-07-30 |  | 2026-07-30 | 1 | REQ CHANGE after deploy
system-config | TimeField replaces every native time input - 12-hour entry everywhere |  | developing | Ashwin | Done | 2026-07-31 |  | 2026-07-31 | 1 | new requirement post-deploy; ESLint rule + test added
timetable | combined teaching: small classes share one session, one teacher, one room |  | developing | Ashwin | Done | 2026-07-31 |  | 2026-07-31 | 1 | new requirement post-deploy
timetable | hour swaps: build the request by clicking a timetable; fix the empty picker |  | developing | Ashwin | Done | 2026-07-31 |  | 2026-07-31 | 1 | part fix, part REQ CHANGE
timetable | period labels derived from the period number |  | debugging | Ashwin | Done | 2026-07-31 |  | 2026-07-31 | 1 | fix on deployed module
dashboard-feed | services grid: drop the hover panel that overlapped the next card |  | debugging | Ashwin | Done | 2026-07-31 |  | 2026-07-31 | 1 | fix on deployed module
attendance | attendance corrections: request dialog rebuilt as a three-step wizard |  | developing | Ashwin | Done | 2026-08-01 |  | 2026-08-01 | 1 | REQ CHANGE after deploy
attendance | combined marking: fix the roster vanishing when the combined fetch lands |  | debugging | Ashwin | Done | 2026-08-01 |  | 2026-08-01 | 1 | fix on deployed module
dashboard-feed | faculty dashboard on real data only - mock data deleted |  | developing | Ashwin | Done | 2026-08-01 |  | 2026-08-01 | 1 | original scope
timetable | close the seams between what is scheduled and what was marked |  | developing | Ashwin | Done | 2026-08-01 |  | 2026-08-01 | 1 | fixes on deployed module
timetable | effective windows: a version applies during its window and nowhere else |  | developing | Ashwin | Done | 2026-08-01 |  | 2026-08-01 | 1 | REQ CHANGE after deploy
attendance | attendance week: a timetable that has not started ran nothing |  | debugging | Ashwin | Done | 2026-08-02 |  | 2026-08-02 | 1 | fix on deployed module
attendance | a holiday owes no register |  | developing | Ashwin | Done | 2026-08-02 |  | 2026-08-02 | 1 | REQ CHANGE after deploy: calendar honoured by attendance
attendance | one card per combined hour, one hero, markable rosters only |  | developing | Ashwin | Done | 2026-08-02 |  | 2026-08-02 | 1 | REQ CHANGE after deploy
timetable | who BUILT a grid is not who published it |  | debugging | Ashwin | Done | 2026-08-02 |  | 2026-08-02 | 1 | fix on deployed module
timetable | publish requires a start date |  | developing | Ashwin | Done | 2026-08-02 |  | 2026-08-02 | 1 | fix on deployed module
attendance | a combined register is one hour, and SLO coverage stops being mandatory |  | developing | Ashwin | Done | 2026-08-03 |  | 2026-08-03 | 1 | REQ CHANGE after deploy: mandatory coverage reversed
attendance | open a single student; a combined correction covers every register |  | developing | Ashwin | Done | 2026-08-03 |  | 2026-08-03 | 1 | new requirement post-deploy
timetable | wrong week schedule and academic year label; course-assigned faculty may cover split/theory periods |  | debugging | Ashwin | Done | 2026-08-04 |  | 2026-08-04 | 1 | fixes on deployed module
timetable | a publish clash says whether it is a room or a faculty |  | developing | Ashwin | Done | 2026-08-04 |  | 2026-08-04 | 1 | fix on deployed module: message was unactionable
attendance | page past PostgREST's ~1000-row cap on unbounded reads (attendance and timetable) |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fix on deployed module: large classes silently truncated
attendance | one register, one marker - an editing claim per class/course/date/period/batch |  | developing | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | new requirement post-deploy: concurrent marking was overwriting
attendance | combined-teaching fallback no longer over-grants split-batch powers; merge/batch race closed at the write |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fix on deployed module
attendance | grid fixes: SLO field visible in every state, Internal Marks reads the class roll number, another course's period opens THAT register |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fixes on deployed module
attendance | hidden admin backfill for classes with no class teacher |  | developing | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | new requirement post-deploy
timetable | clash correctness: day-scoped checks, re-check right before writing, sequential multi-section publish |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fixes on deployed module
timetable | faculty salutation shown everywhere - snapshots, pickers, planners, clash indexes |  | developing | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | new requirement post-deploy
timetable | faculty week: a class reads as the name it is called today; columns are the union of every bell taught |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fixes on deployed module
timetable | builder: fix the merge that broke the module, confirm Save, fix Clear |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fixes on deployed module
timetable | hour swaps: planner resolves both weeks and relays "timetable not started yet"; test coverage added |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fix on deployed module
timetable | Week A/B rotation for labs that alternate Physical/Virtual, plus a session-type colour legend |  | developing | Ashwin | Done | 2026-08-06 |  | 2026-08-07 | 2 | new requirement post-deploy
rooms | teaching-space room-type fallback was missing tutorial/seminar/centre keywords server-side |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fix on deployed module
classes | class teacher picker: department grouping re-homed, match on code as well as name |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | fix on deployed module
class-management | facultyName resolves its own import with an explicit extension |  | debugging | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | build fix
provisioning | provisioning and electives: parallelize sequential per-student round trips |  | developing | Ashwin | Done | 2026-08-06 |  | 2026-08-06 | 1 | performance fix on deployed module
attendance | per-leaf SLO progress; coverage UI skipped for SLO-less courses |  | developing | Ashwin | Done | 2026-08-07 |  | 2026-08-07 | 1 | REQ CHANGE after deploy
attendance | a dispute is answered by whoever was asked, and claimed before acting |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fix on deployed module
attendance | one roster and status rule for both mark writers, and tighter read gates |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fixes on deployed module
elective-timetable | electives: check eligibility before enrolling |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fix on deployed module
timetable | hour swaps: a cancelled swap stops authorizing immediately |  | debugging | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fix on deployed module
timetable | anchor the client's "today" to the server clock (timetable and attendance) |  | debugging | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fix on deployed module
timetable | a fetched teacher is removable everywhere and the removal sticks (theory, lab, tutorial) |  | debugging | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fixes on deployed module
timetable | enforce the publish window and its date bounds on the server, on both doors |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | fix on deployed module: client-only guard
timetable | keep drafts on the server, as a backup and a handover channel |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-09 | 1 | new requirement post-deploy
timetable | printed timetable: notice-board sheet, uniform boxes, titled faculty, print sizing |  | developing | Ashwin | Done | 2026-08-09 |  | 2026-08-10 | 2 | new requirement post-deploy
course | wizard & cards polish: per-module L-T-P entry, curricula-usage count on cards, optional collapsed description |  | developing | George Sebastian | Done | 2026-08-06 |  | 2026-08-06 | 1 | REQ CHANGE after deploy: per-module L-T-P was added, printed and then dropped from the export the same day on owner calls
curriculum | Mandatory Courses + Requisites hardening: MC-only picker, credit feasibility check, fixed-semester error, requisite colouring, Word import |  | developing | George Sebastian | Done | 2026-08-06 |  | 2026-08-08 | 3 | REQ CHANGE after deploy: both new steps reworked days after being added, on review
course plan | §4.5 activity durations, shared CO/SLO coverage, export tree order + CO/micro-SLO gaps fixed |  | debugging | George Sebastian | Done | 2026-08-07 |  | 2026-08-07 | 1 | fixes on the deployed module
course plan | mirror one coordinator's plan to every batch they coordinate + mirror hardening (two-source overwrite, replace target drafts with a report) |  | developing | George Sebastian | Done | 2026-08-07 |  | 2026-08-20 | 14 | new requirement post-deploy: common first-year courses share one authored plan
| user manual written for courses, course plan and assessment |  | support | George Sebastian | Done | 2026-08-08 |  | 2026-08-08 | 1 | documentation for deployed modules
curriculum | PDF export overhaul: Doc No./Version rows, BoS & Academic Council approval dates, per-degree semester count, Part II in reading order with syllabus links |  | developing | George Sebastian | Done | 2026-08-10 |  | 2026-08-14 | 5 | REQ CHANGE after deploy: export metadata respecified repeatedly after the export was approved
course plan | PDF prints §4.2, the P-E-L-C chain and §4.4 (never drawn before); export format v2 carries the whole plan; §4.10 ESE paper with 56 question types |  | developing | George Sebastian | Done | 2026-08-10 |  | 2026-08-11 | 2 | debugging + REQ CHANGE: three sections of the approved PDF had never printed
staff-attendance | COSEC monitor goes live: first real device run, device-user mapping, Schedule tab, Attendance Rules in System Management, seconds-exact thresholds, staff see raw punches |  | developing | George Sebastian | Done | 2026-08-10 |  | 2026-08-13 | 4 | new requirement: punches collected and shown raw, verdicts stay hidden until reviewed
security-admin | security hardening: role never resolved from user_metadata, directory PII reads closed, rate-limited self-registration, IDOR object-level authz audit across the API |  | developing | George Sebastian | Done | 2026-08-13 |  | 2026-08-14 | 2 | security audit on the deployed app — live self-signup escalation found and closed
user-management | granting or removing an admin role takes the acting admin's email OTP + alert emails to the other admins |  | developing | George Sebastian | Done | 2026-08-13 |  | 2026-08-17 | 5 | new requirement post-deploy: no admin change without a second factor
provisioning | provisioning shows and mints the legally verified application-form name |  | developing | George Sebastian | Done | 2026-08-14 |  | 2026-08-14 | 1 | REQ CHANGE after deploy: legal-name policy stated after go-live
user-management | User Directory scoped to one population at a time |  | developing | George Sebastian | Done | 2026-08-17 |  | 2026-08-17 | 1 | REQ CHANGE after deploy: mixed staff/student directory rejected in use
| one loading experience app-wide: Pulse loader + splash that never replays, global search rework, login-page support email button |  | developing | George Sebastian | Done | 2026-08-18 |  | 2026-08-31 | 14 | REQ CHANGE: loader respecified twice on owner review (mark on a white disc)
staff-attendance | four-day COSEC push outage: root cause (.in() id batching), retry-once on transport failure, tombstone run rows, DB-backed machine tokens, module pared down to My Attendance |  | debugging | George Sebastian | Done | 2026-08-18 |  | 2026-08-19 | 2 | outage on the deployed integration — root-caused and hardened
notifications | scope every notification to the people it concerns (164k-row noise purge across 15 segments) + student birthday card no longer shows other students |  | debugging | George Sebastian | Done | 2026-08-18 |  | 2026-08-18 | 1 | REQ CHANGE after deploy: "assignment alert only for its students" — audience model rebuilt
holistic-development | HDP admin: My Units & Events as a table, editor opens in place, unit delete with in-use refusal |  | developing | George Sebastian | Done | 2026-08-18 |  | 2026-08-21 | 4 | original scope
cat | Question Pool rework: one vocabulary, topic picker, model answer, scaffolded scenario type, course-locked authoring, refusal-hang + empty-scheme fixes proven for all 57 types |  | developing | George Sebastian | Done | 2026-08-21 |  | 2026-08-29 | 9 | REQ CHANGE after deploy: the manual's mandatory fields applied after the pool shipped
course plan | §4.6 becomes a CO-organised ESE blueprint; the 40/60 split is one stored number |  | developing | George Sebastian | Done | 2026-08-28 |  | 2026-08-28 | 1 | REQ CHANGE after deploy: flat question pattern replaced by a blueprint after approval
| Phase 1: every client database query moved onto the API (forum, leave, bell, login, appProvider, lookups) + guard test; realtime channels retired; dead tt_* screens deleted |  | developing | George Sebastian | Done | 2026-08-28 |  | 2026-09-02 | 6 | architecture change on the deployed app — client can no longer reach the database directly
| Prisma reaches auth.users + generate on build + /api/health/db; backup downloads stream uncapped on Cloud Run |  | developing | George Sebastian | Done | 2026-08-29 |  | 2026-09-02 | 5 | infrastructure — first step off Supabase
| performance: 18× smaller entry bundle (serviceMeta split + lazy pages), Supabase disk-IO drains cut, audit heartbeat logging stopped |  | developing | George Sebastian | Done | 2026-08-31 |  | 2026-08-31 | 1 | perf work on the deployed app
admission | Phase-1 transport migration: last direct client→DB path closed (owner-sanctioned, transport only) |  | developing | George Sebastian | Done | 2026-09-01 |  | 2026-09-01 | 1 | no admission rule, status or screen changed — only how the bytes travel
course plan | SLH hours read from §4.3 pre/post activities and made compulsory; mirrored-save Cloudflare timeout fix; approval can follow the course's owning HoD |  | developing | George Sebastian | Done | 2026-09-01 |  | 2026-09-03 | 3 | REQ CHANGE after deploy: SLH rule and HoD routing stated after approval
staff-attendance | month navigator on punch history + month-summary end-date fix; cosec-agent moved under ops/ |  | debugging | George Sebastian | Done | 2026-09-02 |  | 2026-09-03 | 2 | fixes on the deployed module
notifications | recall a sent broadcast from every inbox + the bell syncs on open |  | developing | George Sebastian | Done | 2026-09-03 |  | 2026-09-03 | 1 | REQ CHANGE after deploy: a wrong college-wide holiday notice had to be deleted in SQL — recall added after
exam | Exam Creation rework: halls picked from the Rooms service, auto-generated exam name with edit, redundant date picker + Rooms tab removed, full audit on exam_* tables |  | developing | George Sebastian | In progress | 2026-09-03 |  |  |  |  | REQ CHANGE after deploy: separate hall list replaced by the Rooms service on owner call
assessment | question-pool SLO dropdown could read another batch's course-plan version |  | debugging | George Sebastian | Done | 2026-09-04 |  | 2026-09-04 | 1 | cross-batch leak fix on deployed module
admission | Contact number validation incorrectly rejects a valid 10-digit number during Save & Next, blocking progress. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Expected valid 10-digit numbers to be accepted.
admission | Save Draft fails with contact-number validation error even when the entered number is valid. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Admission Form stage indicator does not update according to the current stage. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Top stage navigation allows users to bypass Save & Next validation and move to later stages. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Stage navigation should respect validation rules.
admission | Logout displays “Draft save failed” and cancels logout even when the user expects the session to close normally. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | DOB change-request year field gets cleared / does not allow normal typing. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Employee ID change request unexpectedly changes the applicant DOB. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Date fields can propagate or accept inconsistent dates; add relational validation and a popup for invalid date combinations. |  | testing | Joshua Sony | Done |  |  |  |  | Feature
user-management | Profile photo view option/process is unavailable; only editing is possible. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | After QR scan/activation and program allocation changes, Admission Portal opens directly at Awaiting Program Allocation while Download/Print remain active. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Download/Print should be disabled until the required stage is reached.
admission | Government Quota Registration page gets stuck while scrolling down. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Academic Details correctly blocks Save & Next for ineligible marks, but top stage navigation still allows bypassing the eligibility validation. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Parent/guardian phone numbers can be identical without warning. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Show a duplicate-number warning similar to the applicant contact-number validation.
admission | TC Issue Date year field accepts more than four digits. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Allow exactly four digits for the year.
admission | IFSC Code field does not have proper validation. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | PAN Number field does not have proper validation. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | QR registration/activation flow can encounter a timeout error. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | QR download produces a blurred/unreadable QR code. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
admission | Add applicant count reports by Gender, State, District, Board, Plus Two percentage, Physics/Chemistry/Mathematics marks, PCM percentage bands, Entrance Exam, Entrance Score and Entrance Rank. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Include overall counts and useful filters/breakdowns.
admission | Add program-wise admission counts for B.Tech, M.Tech and Integrated programs, including branch-wise and male/female/overall counts. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Include the requested report structure in Excel export.
admission | Add Excel export for admission reports with Program-wise, State-wise, District-wise, Board-wise, academic marks and entrance-exam sections. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: PCM bands: 90+, 80–89, 70–79, 60–69, below 60; include overall counts.
course | Course Code field is incorrectly limited to 10 characters. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Remove the 10-character limit; allow uppercase letters and digits only.
course | Assessment Pattern automatically assigns total marks as 100 instead of allowing the required marks distribution. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | Add separate assessment fields for CIA Mid-term Test, CIA Assignment(s), CIA Lab Evaluation and ESE Theory, along with Total Marks. |  | testing | Joshua Sony | Done |  |  |  |  | Feature
course | Textbook year field accepts unlimited digits. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Restrict year to four digits.
course | Reference Book year field accepts unlimited digits. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Restrict year to four digits.
course | Header Information → Continue to Syllabus fails with numeric conversion error when a duration is entered as text such as “2 Hours”. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Validate numeric duration fields and prevent invalid submission.
course | Submitting a course to HoD can fail with numeric conversion error when a duration is entered as text such as “2.5 Hours”. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Validate the field format before submission.
course | Academic Management → Programs → PhD → Edit Program fails with “program code is already in use” when updating the existing program. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | Curriculum scheme table columns are not properly aligned by semester. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Use a consistent table structure for Course Code, Course Title, Type, Credits and Exam Slot.
course | Prerequisite tab allows the same course code to be added multiple times. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Once selected, a course should no longer appear in the dropdown.
course | After PC submission, HoD sees ESE-Theory twice even though only one ESE was added. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | Faculty can edit Course Plan even when they are not the Course Coordinator. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Only Course Coordinator should have edit access; other faculty should be view-only.
course | Course Coordinator field in Course Plan shows “Appointed” instead of the assigned coordinator name. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | After HoD approves and submits a course to IQAC, Header Information, Syllabus and Module Contents still show “HoD Approved” instead of “Awaiting IQAC Review”. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | HoD Header Information auto-save fails when navigating back because the Syllabus is already under HoD review. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Avoid attempting edits/auto-save on review-locked sections.
course | HoD rejection message is not shown in Header Information; it appears only in Syllabus and Module Contents. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Show rejection/revision information consistently in the header.
course | View History and HoD Revision Request are combined in one tab. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Create separate tabs; View History should support Hide History, and HoD Revision Request should show revision messages.
course | HoD “Save & Continue?” prompts before Syllabus and Module Contents are unnecessary. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: HoD should begin review from Syllabus and Module Contents rather than Header Information.
course | HoD portal shows unnecessary Save Draft button. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: HoD is reviewing content, not creating it.
course | HoD continuing to Module Contents can fail with “Only the assigned syllabus in-charge can edit this.” |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Review flow should not trigger edit permission errors.
course | HoD-rejected course should allow the faculty to revise Syllabus/Module Contents and resubmit. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Course card should show “HoD Rejected – Requires Revision”.
course | After HoD approval and submission to IQAC, HoD can still edit Syllabus and Module Contents. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: HoD should become view-only after submission to IQAC.
course | Faculty portal shows “Syllabus Editor” and “Awaiting IQAC” after HoD submission to IQAC. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Faculty should not see inappropriate HoD/IQAC approval notifications or editor status.
course | Archived course restore fails because the archived_by column is missing from the schema cache. |  | testing | Joshua Sony | Done |  |  |  |  | Bug
course | Software Admin course delete/archive action fails because the header_draft column is missing from the archived-course schema cache. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Keep the existing archive flow/button and fix the schema issue.
course | Top navigation can bypass Header Information validation and move to Syllabus/Module Contents. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Navigation should be blocked when required fields are invalid.
dashboard-feed | Eye/view icons on Faculty Overview cards are unnecessary. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Clicking the card itself should open the relevant details page; remove the eye icon.
class-management | Class header does not display sufficient subject/class information. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Show Subject Name, Subject Code, Class Name, Subject Type, Staff Advisor, Semester, Academic Year Duration, Semester Duration, Hours and Credits.
class-management | Course Coordinator dropdown differs from Course Faculty and Scrutiny Name dropdowns. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Use the same searchable faculty dropdown component.
class-management | Course Category is not displayed on the Assign Faculty page for batches/classes. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Add Course Category as a visible field/column.
class-management | Maximum Class Strength in the creation popup and Capacity in the preview table refer to the same value but use different terminology. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Use one consistent label throughout the flow.
class-management | “Fix Names” appears beside the batch heading unnecessarily. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Remove the Fix Names option from the batch heading.
user-management | Additional Role and Additional Designation allow only one entry and need Add buttons for multiple values. |  | testing | Joshua Sony | Done |  |  |  |  | Feature: Support multiple additional roles/designations for faculty, lab staff, office staff and other users.
user-management | Maximum Session Limit Reached flow does not log out other active sessions when “Logout all sessions” is selected. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: All other sessions should be terminated and only the current login should remain active.
calendar | Rename the “Everything” filter to “All”. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement
calendar | Month View displays dates from the previous and next months. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Month View should display only dates belonging to the selected month.
calendar | Events are difficult to identify in Month View because day cells have no clear event indication. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Add a colored border around the day cell based on the event/activity color, only in Month View.
calendar | After Google Calendar import, the system redirects to Overview instead of Calendar. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Redirect to the current-day Calendar view and show a success toast for about 2–3 seconds.
calendar | Google Calendar import contains an unnecessary “Choose Calendars” option. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Keep only Import, Clear Imported and Delete.
dashboard-feed | Browser Back from a service subpage returns to the overall Services page instead of the previously visited page. |  | testing | Joshua Sony | Done |  |  |  |  | Bug: Browser Back should follow the actual navigation history.
OBE | OBE version selection is confusing and should be presented before opening the OBE page. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement: Show a version-selection popup when entering the OBE page.
course | Course approval/status messaging should clearly distinguish HoD Rejected, Awaiting IQAC Review and other workflow states. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement
course | HoD review flow should direct reviewers to Syllabus and Module Contents instead of distracting them with editable Header Information. |  | testing | Joshua Sony | Done |  |  |  |  | UI Improvement
admission | Bulk applicant import from CSV fails silently when a row has a malformed date of birth. |  |  | select | Not started
admission | Applicant search does not match on application number, only on name. |  |  | select | Not started
admission | Add a fee-payment status column to the applicant list with a filter for Paid / Pending / Failed. |  |  | select
admission | Uploaded document preview opens in a new tab instead of an in-page viewer. |  |  | select
admission | Withdrawn applications still appear in the active admission count on the dashboard. |  |  | select
course | Course search results are not sorted; results appear in insertion order. |  |  | select
course | Duplicate course codes can be created across two different programs in the same academic year. |  |  | select
course | Add a bulk course import from Excel with a downloadable template and row-level validation report. |  |  | select
course | Course version history does not record who made a change, only when. |  |  | select
course | Syllabus module content editor loses formatting when text is pasted from Word. |  |  | select
course | Credits field accepts negative and decimal values beyond one decimal place. |  |  | select
course | Add a Clone Course action to create a new course pre-filled from an existing one. |  |  | select
class-management | Student list in a class does not show roll number, making manual cross-checking difficult. |  |  | select
class-management | Assign Students screen has no way to remove a student once added. |  |  | select
class-management | Add an Excel export of class-wise student allocation with course and coordinator details. |  |  | select
class-management | Class cards do not indicate how many students are enrolled against capacity. |  |  | select
user-management | Deactivated users can still appear in faculty assignment dropdowns. |  |  | select
user-management | Password reset email link expires without any message explaining why the link failed. |  |  | select
user-management | Add a user activity log showing last login, IP and active sessions per user. |  |  | select
calendar | Recurring events cannot be edited for a single occurrence, only for the whole series. |  |  | select
calendar | Event colour picker resets to the default colour after saving. |  |  | select
calendar | Week View does not highlight the current day. |  |  | select
dashboard-feed | Dashboard cards do not refresh after an action until the page is manually reloaded. |  |  | select
dashboard-feed | Add a configurable dashboard where users can show, hide and reorder cards. |  |  | select
OBE | CO-PO mapping grid does not validate that every CO is mapped to at least one PO. |  |  | select
OBE | Add a PDF export of CO-PO attainment reports with the institution header and signature block. |  |  | select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select
select

## Services
Subjects
Add subjects or courses for the semester
select
academic-management
academics-ops
academic-years
access-check
accounts-hr
admission-approval
admission-completion
admission-dropdowns
admission-services
alumni
assessment
assessment-marks
attainment-cqi
auth
calendar
campus-events
career
cat
classes
class-management
course-builder
course-companion
course-governance
course-offerings
curriculum
curriculum-structure
curriculum-workflow
dashboard-feed
elective-timetable
engagement-hub
events-management
exam
forum
holistic-development
hostel-management
hub
integrations
internship-management
lab-eval
leave
library
mission-vision
notices
notifications
obe-compute
obe-governance
online-assessment
otp
payments
placement
portals-admin
programming-lab
project
provisioning
question-paper
reference-data
research-innovation
responsibility-groups
rooms
security-admin
service-registry
sessions
siee
staff-attendance
student-activation
support-services
syllabus-parser
system-config
teaching
timetable-admin
timetable-coordinators
timetable-days
timetable-periods
transport-management
user-management
select
admission
assessment
forum
course
timetable
course-builder
provisioning
internship-management
curriculum
user-management
course plan
curriculum
OBE
course File
Reports
Feedback Management
library

## Sheet5
Tier 1 — too big for one owner, split further (≥6k LOC)
Module | LOC | Note
admission | 29029 | ⚠️ off-limits per CLAUDE.md — assign as read-only/tracking-only
assessment | 18420
forum | 12932
course | 8836 | server side lives in routes/courses.js (~76KB), add that
timetable | 7785 | plus 4 server services (timetable-admin/-coordinators/-days/-periods)
course-builder | 7587
provisioning | 7136
internship-management | 6639
curriculum | 6639
user-management | 6203
Tier 2 — one solid owner each (1k–6k LOC)
obe · classes · events-management · leave · holistic-development · class-management · course-companion · placement · academic-management · calendar · system-management · programming-lab · service-management · responsibility-groups · moodle-course · staff-attendance · rooms · research-innovation · engagement-hub · hub · exam · project
Tier 3 — small, bundle 2–4 per owner (300–1k LOC)
payments · transport-management · question-paper · branding · attainment-cqi · curriculum-workflow · master-course-management · obe-governance · course-offerings · accounts-hr · support-services · reference-data · assessment-marks · library · notification-management · noticeboard · events · curriculum-structure · academics-ops · portals-admin · security-admin · alumni · attendance · hostel-management
Tier 4 — thin (<300 LOC), likely partial builds
hostel · my-assessments · finance · clubs · library-portal · leave-management · stock · elective-registration · grievance · gate-pass · health-center · canteen · transport · iqac · feedback · purchase · office-management · career-admin · my-timetable · messaging
Not assignable — empty placeholders
auditors · visitor-management · reports-analytics · parent-management · facility-management · external-examiners · digital-learning · alumni-management · accreditation
Two things worth deciding before you hand these out: several client modules are backed by server code that isn't in server/src/services/ (notably course → routes/courses.js, obe → obe-compute/obe-governance), so an owner assigned "course" needs that route file in scope too. And there are near-duplicate pairs — hostel/hostel-management, leave/leave-management, transport/transport-management, alumni/alumni-management, library/library-portal — where the thin one may be a student-facing portal or dead code; give each pair to one owner rather than splitting them.